## Population
2017/18 Work Plan for Population Statistics Team
This document outlines the work which the Population Statistics Team plan to undertake during 2017/18.
This document is considered to be a 'live' document and will be updated to show completion dates etc.
The target dates are estimated based on the current resources available.
Changes to staffing/funding/branch priorities etc may result in amendments to this work plan and these will be highlighted in red below.
A review of user needs against the setting of priorities within this workplan is available here. |  |  |  | Last updated on 30 November 2017
Please email: census@nisra.gov.uk to join our population email distribution list.
1. Population and Migration |  | Start date | Target date | Completed
Publications
1.01 | To consult on, agree and publish Population Statistics Work Plan for 2017-18 | 2017-01-01 | 2016-04-01 | ü
1.02 | To publish 2016 population estimates for Northern Ireland, Local Government Districts, Parliamentary Constituencies, 1992 Electoral Wards and Super Output Areas | 2017-04-01 | 2017-06-01 | ü
1.03 | To update International Migration Tables | 2017-07-01 | 2017-08-01 | ü
1.04 | To publish estimates of the population aged 85 and over for 2015 (NI only) | 2017-07-01 | 2017-09-01 | ü
1.05 | To publish 2016-based population projections for Northern Ireland | 2017-01-01 | 2017-10-01 | ü
1.06 | To publish in tabular format 2016 population estimates for Small Areas and Neighbourhood Renewal Areas | 2017-05-01 | Nov-17 | ü
1.07 | To publish 2016-based population projections for areas within Northern Ireland (down to Local Government District) | 2017-11-01 | Spring-18
1.08 | To commence work on household projections (subject to demand & funding) | - | -
Population Statistics
1.09 | To consider the production of population estimates for the reviewed settlement classifications when the geographic tools become available | 2017-04-01 | 2018-03-01
1.1 | Consider the feasibility of producing population estimates for additional/new geographies (e.g. DEAs) | 2017-04-01 | 2017-12-01
1.11 | For the Registrar General's Annual report: to provide population/migration data, to write population/migration sections, and assist in QA of report | 2017-05-01 | 2017-10-01 | ü
1.12 | To support the review of the Northern Ireland Multiple Deprivation Measure 2010 | 2017-04-01 | Nov-17 | ü
1.13 | To liaise with NINIS to include interactive content and/or infographics in population releases | 2017-04-01 | 2018-03-01
1.14 | To produce and maintain a population statistics manual | 2017-04-01 | Ongoing
1.15 | To issue a new Population Customer Survey | 2017-04-01 | 2018-03-01
1.16 | To implement the agreed User Engagement Strategy | 2017-04-01 | Ongoing
1.17 | To produce articles for NISRA/DFP briefs/magazines | 2017-04-01 | Ongoing
Other Work
1.18 | To keep forthcoming publications up to date on GOV.UK and the NISRA website | 2017-04-01 | Ongoing
1.19 | To maintain the population section of the NISRA website, enhancing where possible and ensuring it is user friendly | 2017-04-01 | Ongoing
1.2 | To respond to ad hoc queries, AQs, PQs, etc | 2017-04-01 | Ongoing
1.21 | To attend and contribute to UK meetings on population, household and migration statistics | 2017-04-01 | Ongoing
1.22 | Staff development, branch meetings etc | 2017-04-01 | Ongoing

## User Needs Summary
User Needs Summary
The work plan is decided upon by reviewing user needs with regards to population and migration statistics and requests relating to this, e.g. Geographies, age-sex breakdowns, etc. in conjunction with resources and data available, collaboration with statistical organisations across the UK, and events that impact production, e.g. Release of Census results leading to time made for methodological review and resulting improvements to releases.
The workplan has been reviewed and is based on information received by key users at the most recent User Engagement Event in January 2016.
(Event summary details available)
Publication | Target Date | User Need
Mid-Year Population Estimates | 2017-06-22 | Population statistics for Northern Ireland will be published in June to coincide with the ONS release of estimates, allowing the publication of a UK figure at the same time.
- Includes statistics for NUTSIII, Health Areas, Education and Library Boards, 11 new Local |  | Former Local Government Districts are still currently produced in order to meet user need for statistics at other higher geographies, e.g. NUTSIII
Government Districts, Parliamentary Constituencies, Former Local Government Districts,
Electoral Wards and Super Output Areas |  | Methodological updates as a result of the 2011 Census release mean that estimates for Electoral Wards and Super Output Areas are available to users for release earlier in the year in June, instead of at a later date in the year.
Migration Statistics | 2017-08-31 | Published in in August to allow for the most comprehensive and recent administrative data to be collected for comparison with official migration estimates
Estimates of the Population Aged 85 and Over | 2017-09-27 | Publication date is collaborated across the UK to have the latest available statistics available for International Older People's Day (1st October).
- Includes analysis, as well as methodological and quality information. |  | Further analysis and additional sections on data quality, methodology and limitations were added as a result of the recent UKSA assessment.
Population Estimates for Small Areas | 2017-11-01 | A quality review was held of the Census Small Areas and it was decided that due to their small size, these estimates benefit from an extra quarter of administrative data for quality assurance. In order to ensure users have the best quality statistics, a later release of November was agreed upon for this publication. it was also agreed with users in January 2016 that this release would take the form of statisticsl tables only.
-Includes statistics for Neighbourhood Renewal Areas (NRAs) |  | The methodological review also results in NRAs being aggregated from Census Small Areas and therefore are to be released alongside them to produce the most accurate statistics.
Population Projections for Northern Ireland | 2017-10-26 | National population projections are produced biennially on behalf of Northern Ireland by ONS, and are agreed upon by users and statistical organisations across the UK.
Population Projections for Areas Within Northern Ireland | Spring-18 | Sub-national projections are based on the projections for Northern Ireland and therefore follow the same biennial time release agreed upon by users and statistical organisations for the National Projections, in order to allow for quality assurance and methodological discussions to be realised across the UK.
Work on the sub-national projections are planned for production following the release of the National projections in October 2017, and the Population Estimates for Small Areas in November 2017. Given the work involved, publication is currently planned for Spring 2018.
Household Projections | Ongoing | Household projections are subject to user need and funding and work on these will be commenced if these conditions are met.
Household Projections are based on the sub-national population projections and therefore also follow the biennial time release schedule agreed upon for the National Projections.